{"text_format":"2","workbook":"xlsx","n_sheets":1,"sheets":["Sheet1"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":0,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Sheet1","index":0,"n_rows":12,"n_cols":12,"rows_kept":12,"cut":false,"hidden":false,"merged":[[11,0,11,4],[12,0,12,4],[13,0,13,4],[5,1,9,1],[5,2,9,2],[4,0,4,4],[0,0,0,12],[2,0,3,0],[2,1,3,1],[2,2,3,2],[2,3,3,3],[2,4,3,4],[2,5,3,5],[2,6,2,9],[2,10,3,10],[2,11,3,12]]}
["Function List"]
[]
["序号","功能模块","子功能模块","二开概要功能点","概要任务说明","备注","项目开发阶段",null,null,null,"功能风险度","合计"]
[{"$nulls":6},"明细需求","程序开发","单元测试","集成测试"]
["开发活动工作量小计：",{"$nulls":5},{"$f":"SUM(G6:G10)","v":3},{"$f":"SUM(H6:H10)","v":35},{"$f":"SUM(I6:I10)","v":8.5},{"$f":"SUM(J6:J10)","v":3},null,{"$f":"SUM(L6:L10)","v":49.5}]
[1,"成本管理","人工成本管理","门店基础信息维护","1、可导入，可单独添加，接楼时间和开业时间允许调整，并保留调整记录。（导入需校验代码和名称与HR是否一致，所以项目开始筹备前，需在HR系统中新增架构）\n2、导入/修改后，点击按钮生成筹备期和开始筹备月份，系统根据筹备原则，生成筹备期和开始筹备月份。\n3丶如果修改了开业时间，需要提相关人员，发消息到企业微信，弹框选人可以多选，点发送。",null,1,10,4,1,"可控（需求明确）",{"$f":"G6+H6+I6+J6","v":16}]
[2,null,null,"原则配置界面","1、用于条件和规则配置.",null,0.5,3,0.5,0.5,"可控（需求明确）",{"$f":"G7+H7+I7+J7","v":4.5}]
[3,null,null,"人工预算值及实际值维护","1.用于预算负责人维护门店的当年度的人工成本预算和实际完成情况，如有更新，仅从当前月份更新。",null,0.5,6,1,0.5,"可控（需求明确）",{"$f":"G8+H8+I8+J8","v":8}]
[4,null,null,"人员配置进度维护","1.用于BP负责人维护门店人员配置计划，如果有更新，仅能从当前月份更新，已发生月份不能更新。如果开业时间有延期，月份要新增导入。 可以先导出所有，然后再新增行，再导入。全部覆盖导入。",null,0.5,6,1,0.5,"可控（需求明确）",{"$f":"G9+H9+I9+J9","v":8}]
[5,null,null,"报表:人员及成本跟踪","1.根据已维护数据和系统人事信息基础数据，以店为单位生成人员成本跟踪表。",null,0.5,10,2,0.5,"可控（需求明确）",{"$f":"SUM(G10:J10)","v":13}]
[]
["开发活动工作量小计：",{"$nulls":5},{"$f":"SUM(G6:G10)","v":3},{"$f":"SUM(H6:H10)","v":35},{"$f":"SUM(I6:I10)","v":8.5},{"$f":"SUM(J6:J10)","v":3},null,{"$f":"SUM(L6:L10)","v":49.5}]