{"text_format":"2","workbook":"xlsx","n_sheets":1,"sheets":["开发计划"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":6,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"开发计划","index":0,"n_rows":9,"n_cols":14,"rows_kept":9,"cut":false,"hidden":false,"merged":[[0,0,0,13]]}
["天虹月薪标准配置开发主体计划"]
["WBS","里程碑","关键路径","任务","需求","设计","开发","测试","部署","合计","责任方","金蝶方责任人","客户方责任人","备注"]
[1,null,"是","全新业务单据开发"]
[1.1000000000000001,"★","是","月薪标准配置",1,1,4,1,0.5,{"$f":"SUM(E4:I4)","v":7.5}]
[2,0,"是","shr标准单据维护"]
[2.1,null,"是","员工信息维护-薪酬福利表 新增两个月薪标准值字段",0,0,1,0.5,0,{"$f":"SUM(E6:I6)","v":1.5}]
[2.2000000000000002,null,"是","人力资源共享-入职办理 新增两个月薪标准值字段，增加弹出提示框。",0,0,1,0.5,0,{"$f":"SUM(E7:I7)","v":1.5},"金蝶","刘璨"]
[2.2999999999999998,null,"是","员工管理-入职-工作流入职 新增两个月薪标准值字段，增加弹出提示框。",0,0,1,0.5,0,1.5,"金蝶","刘璨"]
[{"$nulls":9},{"$f":"SUM(J3:J8)","v":12}]